## Cover
SHEPHERD CONNECT
Implementation Plan — Rollout to RCCG City of David
Safe. Known. Celebrated.
HOW TO USE THIS PLAN
This workbook covers every step needed to go from today to Official Activation on the 1st Sunday of September.
Navigate each sheet in order. Responsible parties are named. Dates are relative to Activation Day.
Sheet | Contents
Cover | You are here — overview and how to use this file
Master Timeline | Week-by-week Gantt of all phases from now to activation
Phase 1 Sensitise | Engage and onboard teachers; create church-wide awareness
Phase 2 Pilot | 10-family pilot: what to do, when, who is involved
Phase 3 Feedback | Collect pilot feedback, iterate, prepare announcement
Phase 4 Pastoral | Presentation to Pastorate for sign-off
Phase 5 Activate | Official activation on 1st Sunday September + go-live checklist
RACI | Who is Responsible, Accountable, Consulted, Informed for each task
Target Activation Date | 1st Sunday, September 2026
Document owner | Admin / Implementation Lead

## Master Timeline
MASTER TIMELINE — Shepherd Connect Rollout to Activation (1st Sunday September 2026)
All weeks are approximate. Adjust to match your actual church calendar.
Phase | Activity | Owner | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5-6 | Wk 7-8 (LIVE)
Phase 1 Sensitise | Teacher briefing meeting | Admin | Y
| Teacher onboarding (accounts + app walkthrough) | Admin + IT | Y | Y
| Church-wide awareness (bulletin, announcement) | Admin + Pastor |  | Y | Y
| QR code / flyer distribution to families | Admin |  |  | Y
Phase 2 Pilot | Select 10 pilot families | Admin |  |  | Y
| Pilot families: register and add children | Parents (guided) |  |  | Y
| Pilot Sunday 1 — check-in and check-out drill | Admin + Support |  |  |  | Y
| Pilot Sunday 2 — teacher confirmation drill | Teachers + Admin |  |  |  | Y
| Pilot Sunday 3 — delegate OTP pickup test | Admin + Support |  |  |  |  | Y
Phase 3 Feedback | Collect feedback from pilot families | Admin |  |  |  |  | Y
| Collect feedback from teachers | Admin |  |  |  |  | Y
| Review and fix issues raised | IT / Admin |  |  |  |  | Y
| Prepare announcement script (based on feedback) | Pastor / Admin |  |  |  |  | Y
Phase 4 Pastoral | Prepare presentation deck for Pastorate | Admin |  |  |  |  | Y
| Present to Senior Pastor / Pastorate for sign-off | Admin Lead | [5 empty] | Y
| Receive approval and set Official Activation date | Pastor + Admin | [5 empty] | Y
Phase 5 Activate | Full-church announcement (Sunday service) | Pastor | [5 empty] | Y
| All families register (open enrollment) | All Parents | [5 empty] | Y
| All teachers fully on-boarded | Admin | [5 empty] | Y
| OFFICIAL ACTIVATION — 1st Sunday September | All Roles | [5 empty] | LIVE

## Phase 1 Sensitise
PHASE 1 — SENSITISE: Teacher Onboarding and Church Awareness
Objective: Every teacher knows the app, has an active account, and the congregation knows Shepherd Connect is coming.
# | What to do | When | What is required | Who is involved
1 | Hold a Teacher Briefing Meeting Introduce Shepherd Connect — purpose, features, and the teacher role in the system. | Week 1 | Projector or TV screen Demo login: teacher1@shepherd.com Printed one-page overview Meeting room booked | Admin Lead Senior Teacher Pastor (optional opening prayer)
2 | Create teacher accounts Each teacher self-registers with role = Teacher. Admin approves each account in the Users tab. | Week 1-2 | Teachers have smartphones with a browser App link shared via WhatsApp or email Admin ready to approve accounts on the spot | All Teachers Admin (for approvals)
3 | App walkthrough with teachers Live demo: My Class, Attendance, Appraisals, Class Change Requests. Teachers follow on their own phones. | Week 2 | App running on a shared screen Teachers follow on their own phones Q&A time built in (allow 30 min) | Admin Lead IT Support All Teachers
4 | Church bulletin and announcement Announce the upcoming rollout. Something exciting is coming to Children's Church. | Week 2-3 | Bulletin insert designed and printed Announcement script prepared for Sunday service Social media post (if applicable) | Admin Pastor or MC Media Team
5 | Distribute parent awareness materials QR code posters in children's church area, flyers for families to take home. | Week 3 | QR codes printed pointing to registration page Flyer explaining what Shepherd Connect does for parents Staff available to answer questions after service | Admin Support Staff Children's Church Ushers
6 | Set up all classes and class assignments Ensure every child is in the correct class in the system before the pilot begins. | Week 3 | Admin access to the app Class structure agreed with senior teacher All existing children registered in system | Admin Senior Teacher
TIP: Use the teacher1@shepherd.com demo account for all demos. Have the admin approve new teacher accounts on the spot — it takes 30 seconds.

## Phase 2 Pilot
PHASE 2 — PILOT: 10-Family Live Test (3 Practice Sundays)
Objective: Iron out any issues before full rollout. Pilot families experience the full journey — registration, check-in, escort, pick-up, delegate OTP, and appraisals.
# | What to do | When | What is required | Who is involved
1 | Select 10 pilot families Choose a mix: different class ages, at least 2 families with delegates, 1 with a medical alert on file. | Week 3 | Admin decides selection criteria Families notified and briefed via WhatsApp Their children already added to the system | Admin Lead Senior Teacher
2 | Pilot families register parent accounts Guided session — parents create accounts, see their child profiles, and explore the app. | Week 3 | Parents have smartphones App link shared in advance Admin on standby to help with registration Children's profiles verified in system | All 10 Pilot Families Admin + Support Staff
3 | PILOT SUNDAY 1 — Check-in drill Scan QR, check children in, walk them to class, confirm arrival in app. | Week 4 | Support staff at check-in desk with a device QR codes for pilot family cards Admin monitoring dashboard live Teachers confirm children arrive in class | Support Staff (check-in) Admin (monitoring) All Teachers 10 Pilot Families
4 | PILOT SUNDAY 2 — Teacher confirmation drill Teachers mark attendance live. Test the class change request flow. | Week 4 | Teachers logged in on their phones during service Admin reviews class change requests in real-time Note any UX confusion or errors | Teachers Admin 10 Pilot Families
5 | PILOT SUNDAY 3 — Delegate OTP pickup test At least 2 families use a delegate. Attendant verifies OTP at the gate. | Week 5-6 | Pilot families pre-add a pickup delegate in app OTP shown and copied before Sunday Support staff use Delegate OTP Checkout tab at pick-up | Support Staff (checkout) Admin 2+ Pilot Families with delegates
6 | Appraisal test Teachers submit appraisals for pilot children. Parents check that they received the notification. | Week 5-6 | Teachers log in after service Write at least 1 appraisal per child Parents confirm they received the notification | All Teachers 10 Pilot Families
7 | Document issues and fixes Log any bugs, confusion, or missing features encountered during the pilot. | Week 5-6 | Simple issues log (WhatsApp group or spreadsheet) IT team addresses any bugs between pilot Sundays Admin notes process gaps | Admin IT / Developer All Pilot Participants
TIP: Keep a shared WhatsApp group with pilot families throughout. It is the fastest way to collect real-time feedback and resolve confusion.
TIP: Ask pilot families to screenshot any error or confusing moment — these become the most useful feedback.

## Phase 3 Feedback
PHASE 3 — FEEDBACK, ITERATION AND ANNOUNCEMENT PREP
Objective: Gather structured feedback from pilot families and teachers, fix issues, then prepare the church-wide announcement using real pilot outcomes.
PART A — PILOT FAMILY FEEDBACK (collect via WhatsApp, Google Form, or in person)
Question | Answer options
How easy was it to register and add your child? | 5 stars / 4 stars / 3 stars / 2 stars / 1 star
Did you receive a notification when your child was checked in? | Yes, immediately / Yes, but late / No
How confident did you feel using the app on Sunday? | Very confident / Somewhat confident / Needed help / Struggled
Did the delegate OTP pickup work smoothly? (if applicable) | Yes / No / Did not use this feature
What was the most useful feature? | Open text
What was the most confusing part? | Open text
Would you recommend Shepherd Connect to other families? | Definitely / Probably / Not sure / No
Any other comments or suggestions? | Open text
PART B — TEACHER FEEDBACK
Question | Answer options
How easy was the app to use on a Sunday morning? | 5 stars / 4 stars / 3 stars / 2 stars / 1 star
Did you find My Class helpful for managing children? | Very helpful / Somewhat / Not really
Did appraisals take too long to complete? | No, quick and easy / A little slow / Yes, too long
Did you have any issues with class assignments? | None / Minor issues / Major issues (describe below)
What would make this app more useful for teachers? | Open text
PART C — ANNOUNCEMENT PREPARATION CHECKLIST
Item | Owner | Status
Review feedback summary (top 3 positives + top 3 issues) | Admin | Not started
Fix critical issues raised in pilot | IT / Developer | Not started
Draft announcement script for Sunday service (quote real pilot feedback) | Admin + Pastor | Not started
Prepare 2-slide visual for announcement (optional) | Admin / Media Team | Not started
Add announcement to Sunday bulletin | Admin / Bulletin Team | Not started
Prepare pastoral presentation (for Phase 4 sign-off) | Admin Lead | Not started

## Phase 4 Pastoral
PHASE 4 — PASTORAL PRESENTATION AND SIGN-OFF
Objective: Present the system, the pilot outcomes, and the rollout plan to the Senior Pastor and Pastorate — and get official sign-off to activate.
# | What to do | What is required | Who is involved
1 | Schedule the pastoral meeting Request 20-30 minutes on the Pastorate agenda — allow at least 1 week's notice. | Diary access for Pastorate Agenda item submitted in advance | Admin Lead Pastor's PA or Secretary
2 | Prepare the presentation Cover: What is Shepherd Connect, pilot results, feedback highlights, activation plan, costs. | Pilot feedback summary (from Phase 3) Cost summary from Annual Cost Planner Shepherd Connect demo available on a device Printed 1-page summary as a leave-behind | Admin Lead IT / Developer (for demo support)
3 | Deliver the presentation Walk through: problem, solution, pilot outcome, feedback, activation date, and cost. | Laptop or tablet for live demo Printed one-pagers Time: 20 min presentation + 10 min Q&A | Admin Lead Senior Teacher (to speak to teacher experience) IT Support (on standby)
4 | Receive pastoral questions and address concerns Common questions: data privacy, cost, what if app is down, how parents register. | Prepared FAQ sheet (see below) Annual Cost Planner open on a device Know who handles technical issues | Admin Lead Pastor / Pastorate Members
5 | Receive sign-off and set official date Get verbal or written approval. Confirm 1st Sunday September as activation date. | Meeting minutes or approval email drafted in advance Activation date confirmed with children's church schedule Communicate approval to all relevant teams | Senior Pastor Admin Lead
SUGGESTED FAQ SHEET FOR PASTORATE
Question the Pastor may ask | Suggested answer
Is children's data safe? | All data is stored securely in a private database. Only authorised staff (admin, teachers, support) can see child records. Parents only see their own children.
What happens if the app goes down on Sunday? | We keep a paper register as backup. Once the app is restored, data is entered manually. The system has been tested over 3 pilot Sundays without any downtime.
How do parents sign up? | Parents register with their email and phone number. They are shown only their own children. No technical skill is needed — it works like any church app.
What is the cost? | Approximately $194 per month (or about NGN 314,000 per month at current rates). This covers hosting, SMS check-in alerts, and email reports. A full breakdown is in the Annual Cost Planner.
Who manages the system? | The Children's Admin manages day-to-day operations. IT support handles any technical issues. Shepherd Connect has a dedicated support guide for every staff role.

## Phase 5 Activate
PHASE 5 — OFFICIAL ACTIVATION: 1st Sunday September 2026
Objective: Full church goes live on Shepherd Connect. Every family registered. All staff at posts. Check-in desk operational from day one.
PRE-ACTIVATION WEEK CHECKLIST — Complete by Saturday before Activation Sunday
Done? | Task | Owner | Notes
[ ] | All teacher accounts created and approved | Admin
[ ] | All children registered and in correct classes | Admin + Teachers
[ ] | Class assignments reviewed with senior teacher | Admin + Senior Teacher
[ ] | Support staff briefed on check-in and check-out procedure | Admin
[ ] | Check-in desk device(s) charged and logged in | Support Staff
[ ] | QR code cards printed for all registered families | Admin
[ ] | Backup paper register printed for check-in desk | Admin
[ ] | All pilot family feedback issues resolved | IT / Developer
[ ] | Announcement prepared for Sunday service | Pastor / MC
[ ] | Family registration link shared via WhatsApp and bulletin | Admin
[ ] | Admin logged in and monitoring dashboard from start of service | Admin
ACTIVATION SUNDAY — ROLE ASSIGNMENTS
Post | Role / Person | Responsibility
Check-in Desk | Support Staff (2 people) | Scan QR codes, check in all children, handle walk-in families who need to register on the spot.
Church Entrance | Ushers / Support | Direct families to check-in desk. Hand out QR card if family has none.
Each Classroom | Class Teacher | Confirm children arrive (mark in app). Run class as normal. Write appraisals after service.
Escort Corridor | Support Staff | Escort children from lobby to classrooms. Mark In Transit in the app.
Pick-up Desk | Support Staff (2 people) | Verify parent identity, confirm pickup in app. Handle delegate OTP if applicable.
Monitoring Dashboard | Admin | Watch live dashboard for any child not yet collected. Trigger late-pickup alerts if needed.
Helpdesk / Registration | Admin + IT | Help families register on the spot. Resolve any app issues immediately.
POST-ACTIVATION WEEK — FOLLOW-UP TASKS
# | Task | Owner
1 | Review first-Sunday attendance data in Reports tab | Admin
2 | Collect any remaining family registrations (follow-up WhatsApp) | Admin
3 | Address any issues raised by staff or parents on Day 1 | Admin + IT
4 | Send a Thank You notification to all parents via app broadcast | Admin
5 | Debrief meeting with teachers and support staff (15 min) | Admin Lead
6 | Share first-Sunday summary with Pastorate | Admin Lead

## RACI
RACI MATRIX — Responsibility Assignment for Shepherd Connect Rollout
R = Responsible (does the work) A = Accountable (owns the outcome) C = Consulted I = Informed
Task | Senior Pastor | Admin Lead | Teacher | Support Staff | IT / Developer | Parents
Define rollout timeline and milestones | A | R | I | I | C
Teacher briefing and onboarding | I | R/A | C
Approve teacher accounts in system |  | R/A | I
Set up classes and assign children |  | R/A | C
Select 10 pilot families |  | R/A | C | I
Register pilot families in app |  | C |  | R |  | A
Pilot Sunday check-in operations |  | I | R | R | I | C
Pilot Sunday class confirmation |  | I | R/A | I
Collect pilot feedback |  | R/A | C | C |  | C
Fix bugs and technical issues |  | A |  |  | R
Draft church-wide announcement | A | R
Prepare pastoral presentation |  | R/A | C |  | I
Present to Pastorate and get sign-off | A | R
Pre-activation setup and checks |  | R/A | C | C | C
Activation Sunday check-in desk |  | I |  | R/A
Activation Sunday class management |  | I | R/A | I
Activation Sunday monitoring dashboard |  | R/A | I | I | I
Post-activation debrief and report | I | R/A | C | C | C
Ongoing: weekly attendance and appraisals |  | A | R | R |  | I
Ongoing: broadcast notifications to parents |  | R/A |  |  |  | I
Ongoing: approve class change requests |  | R/A | C |  |  | I
Ongoing: cost management and top-ups |  | R/A
Where two roles share responsibility (R/A), both are accountable but one person leads. Agree in advance who leads each task.